# Project management body of knowledge

### Executive summary

This passage will explain in detail the steps that will be undertaken in order to successfully complete the Launching of Magazine. As the school wishes to launch a magazine, all the necessary steps such as Time - scheduling, Work Break-Down Structure, Cost Break-Down Structure are explained in detail below.

The rest of the report encounters the risks that can or are been taken place while the project and the way they are been tackled to overcome the hurdles in between of the completion of the project. There are also ways of communication, delegation, motivation and other types of tools given in the passage that help the author to manage his team properly

### 1) Introduction

.According to the PMBOK (Project Management Body of Knowledge) (1996), “A project is a temporary endeavor undertaken to create a unique product or service. Temporary means that every project has a definite beginning and a definite end unique means that the product or service is different in some distinguishing way from all similar products or services”

Similarly, “A project is a set of people and other resources temporarily assembled to reach a specified objective, normally with a fixed budget and with a fixed time period. Projects are generally associated with products or procedures that are being done for the time or with known procedures that are being altered”.Graham (1985)

The accomplishment of any project depends on the way it is been designed, carried out and controlled. If these three are been, taken care of then the project will successfully complete with its satisfactory outcomes.

### 2) Background review

The author is studying in a college the name of the college is “RIMS INTERNATIONAL SCHOOL AND JUNIOR COLLEGE” the author is the member of Student Council(group of student who are given duties responsibility  to conduct an event) of the school and has been given a project of publishing a new STUDENT'S MAGAZINE. The author is currently working on this new project.

### 3) Goals and objectives of the project

The desired or needed result to be achieved by a specific time. An objective is broader than a goal, and one objective can be broken down into a number of specific goals. - Laura Lake

The objectives of this project are:

- To give students the opportunity  to show the creativity and their knowledge

- To improve the communication skills and relationship between teachers and students

- Raise finance for the social causes from the profit earned by this project.

- Time take : - approximate 57 days.

- Start - date  : - 1st April 2010.

- End - date  : - 27 May 2010

### 4) Project Scope

PMBOK (1996) states that “Scope management is the process required to ensure that the project includes all the work required, and only the work required, to complete the project successfully. It is primarily concerned with defining and controlling what is or is not included in the project.”

This complete project demonstrates the essential steps that need to be undertaken in order to launch a student's magazine. This report shows all the essential steps along with a cost budget, time scheduling and resource planning for the school in order to have a successful student's magazine. It also shows any obstructions that may occur in the future and steps to follow in order to overcome these obstructions.

### 5) List of Activities

1. Brainstorming

A. Inform principal about the ideas of the project

B. Generating ideas of themes/genres for magazine

C. Meeting with students

D. Ideas discussion with teachers

E. Confirmation by project manager

### 2. Planning

Budget

F. Making list of the costs in the project

G. Meeting with the teachers, students and principal for the approving the budget.

H. Finding the sponsors for financial support

I. Meeting the sponsors and convincing them to finance the project

Articles

J. Deciding types of articles required

K. Informing to students for the articles

L. Laying deadlines for submission of articles

M. Collecting the articles

N. Sorting the articles according to genres

O. Selection of the appropriate articles to be printed

P. If not appropriate then re writing of articles

### 3. Promotion

Q. Deciding the type of promotion to be used

R. Making design of the charts

S. Uploading it on the college walls and outside the college in college banner

### 4. Design of the magazine

T. Contacting a professional magazine designer

U. Deciding the theme of the magazine

V. Select appropriate theme for the magazine with a meeting with the project manager

W. Send the data to the designer for the final arrangement

X. Proof reading 1st time

Y. Final reading

Z. Launching the magazine

### 6) Work Break Down Structure (WBS)

Turner (1993) says, “A WBS is a cascade of deliverables, in which the overall product or objective of the project is broken into sub-products, assemblages and components.”

The WBS is a hierarchical structure, which is best presentation by a graphical subdivision of the scope of work in boxes. This logical subdivision of all the work elements is easy to understand and assimilate, thus helping the project participants to quantify their responsibility and gain their commitment and support.

-Burke R. (2003)

In the given figure 1.2, all the important tasks are divided into smaller groups. This subdivision will help the project manager to understand the tasks appropriately and then delegate them after considering the capability and efficiency of different group members who will be able to carry out these delegated tasks.

### 7) Time Scheduling Table

| Activity no | Dependent | Duration | Start date | Finish date |
| --- | --- | --- | --- | --- |
| 1 Brainstorming |  |  |  |  |
| A | - | 2 | 1/4/2010 | 2/4/2010 |
| B | A | 3 | 3/4/2010 | 5/4/2010 |
| C | - | 1 | 3/4/2010 | 3/4/2010 |
| D | B,C | 1 | 4/4/2010 | 4/4/2010 |
| E | D | 1 | 5/4/2010 | 5/4/2010 |
| 2Planning |  |  |  |  |
| Budget |  |  |  |  |
| F | E | 5 | 6/4/2010 | 10/4/2010 |
| G | F | 1 | 11/4/2010 | 11/4/2010 |
| H | G | 7 | 11/4/2010 | 17/4/2010 |
| I | H | 10 | 17/4/2010 | 26/4/2010 |
| Articles |  |  |  |  |
| J |  | 2 | 6/4/2010 | 7/4/2010 |
| K | J | 3 | 8/4/2010 | 10/4/2010 |
| L | K | 1 | 11/4/2010 | 11/4/2010 |
| M | L | 7 | 21/4/2010 | 27/4/2010 |
| N | M | 3 | 28/4/2010 | 30/4/2010 |
| O | N | 5 | 1/5/2010 | 5/5/2010 |
| P | O | 10 | 6/5/2010 | 15/5/2010 |
| 3 Promotion |  |  |  |  |
| Q | - | 3 | 12/5/2010 | 14/5/2010 |
| R | Q | 10 | 15/5/2010 | 24/5/2010 |
| S | R | 2 | 25/5/2010 | 26/5/2010 |
| 4 Design of the magazine |  |  |  |  |
| T | S | 3 | 6/5/2010 | 8/5/2010 |
| U | T | 3 | 9/5/2010 | 11/5/2010 |
| V | U | 1 | 12/5/2010 | 12/5/2010 |
| W | U | 7 | 13/5/2010 | 19/5/2010 |
| X | W | 3 | 20/5/2010 | 22/5/2010 |
| Y | X | 2 | 23/5/2010 | 24/5/2010 |
| Z | Y | 1 | 31/5/2010 | 31/5/2010 |

Figure 1.3: Time Schedule table for Magazine. (Field work)

### Analysis of time scheduling

Time scheduling of every activity that needs to be undertaken is mentioned above and timed appropriately in order to slack any overlapping of activities.

The graph drawn in figure 1.3 is the representation of a time schedule. This is a very simple method to represent the time allocated to every task. It helps to show when a task starts, when it ends, the duration of the task and any overlapping of tasks. The author has used time scheduling for the project to improve his time management. Use of this as a plan will give deadlines of every task to team members. Since all the activities are interrelated every team needs to understands that if they don't complete their work on time then the other team members cannot complete their work as well, therefore everyone would motivate each other to work hard and try to complete the task as soon and as better as possible.

### 8) Cost Break-down Structure (CBS)

Cost break down structure represents the financial breakdown of the project into budget per worker package.

-Burke R. (2003)

It is very important for a project as the entire project depends on the budget made. Cost budget mainly helps in breaking down the things that will require finance and it also helps in showing the amount of finance required for a list of Activities prepared. After making a CBS, it will become easier for the project manager to cut the costs or find any other possible option if possible in order to work within the budget.

### CPA analysis

### Budget of the project = 4, 00,000

### Cost of the project = 1, 63,000

Profit = 2, 37,000

Note:- the profit earn by the project can be utilized in many things like school repair, buy new sports equipments, use it for next year's school magazine, and as per the  one of the objectives social welfare can also be done.

### 9) Critical path analysis

Critical Path Method (CPM) is a procedure for using network analysis to identify those tasks which are on the critical path: i.e. where any delay in the completion of these tasks will lengthen the project timescale, unless action is taken.

According to Burke (2003), “A Network diagram is a development of the active-on-node concept where each activity is represented as a node or a box.”

Using of a CPA in a project helps in calculating the total project duration, earliest start time (EST) for each activity, latest finish time (LFT) of each activity, the manager will be able to see whether the project is on plan or not.

### Analysis of the CPA

The network diagram given, figure 1.5, is made for this project. It shows which activity is dependent on what and it helps the manager to keep a record of whether the tasks completing on time or not. The author has used the critical path to show how the team how to executed the project.

### 10) Gantt Chart

Gantt chart is a bar chart that shows the whole schedule the project. It is been named after Henry Gantt who designed it in between 1910-1915. This chart shows the starting and ending of the task along with the dates of the project. It also shows the dependence of an element with another in the given activities. With the use of Gantt chart we can view the present progress of the project also.

### NOTE due to the huge size of the chart it cannot be displayed in this words file it is made in excel sheet.

### 11) Risk-assessment

According to Burke (2003) Page 99, the risk management plan include the process of identifying, analyzing and responding to project risks. It consist of risk identification, risk qualification and the impact, response development and risk control. It should also include a disaster recovery plan to accommodate the worst possible scenario.

| Risk description | Potential effects | Risk likelihood (1-3, 3 being the highest) | Risk impact (1-3, 3 being the highest) | Actions required to mitigate risks |
| --- | --- | --- | --- | --- |
| Improper theme | On the whole project | 2 | 3 | Contact a professional agency |
| Not having a appropriate funds as per the budget | On the whole project | 3 | 3 | Can have outside sponsors |
| Not getting sponsors | Funds for the project will get less | 3 | 3 |  |
| Not getting the articles on time | Delay on publishing the magazine | 3 | 3 | Give dates before deadline or can keep teachers of helping students technically |
| Not having enough funds for Promotion of the magazine | Students will not be persuaded and motivates to write a good article | 1 | 1 | Can make announcements in classes and can even have a small meeting after school to motivate students |
| Design of the magazine is not appropriate | Effect on schools name and reputation | 2 | 3 | Can keep one more professional agency as a backup |
| Delay in printing | Delay in launching the magazine | 2 | 3 | Give the formatted articles as soon as possible. |

Figure 1.6: Risk Assessment table for the Magazine (fieldwork)

The success or the failure of the project is completely depended on how the team handles all the risk mentioned above. If all the risks are handled properly then there is no chance to fail. The author had conducted the risk assessment to reduce the chances of failure of the project

### 12) Roles and responsibility

The organization structure according to Mullins: the structure is important for any organization irrespective of the size of the business; small businesses are likely to have fewer problems. The distribution of tasks, the definition of authority and responsibility increases with the size of the organization and that also increases the level of risk to handle the organization structure.

-Mullins, L.J., 2007

My post in this project was to manage the entire team as a team leader. A team manager is the main person in charge of the entire project and has to be report about all the details. Below him come the two-team leaders and one assistant. The main role of the assistant is to communicate with the two-team leaders and inform every detail of the task beginning till completion. The two-team leaders and two teachers are responsible to finish the specific tasks that are been delegated to them. Their responsibility is to manage the three-team members below them and to keep a record of what and how the team members perform. In addition, below the assistant would be the magazine designer who will make the final design of the magazine. The organizational structure shown below is been made for the project. The benefit of making this diagram is to show the significance of all the members where they are placed in the graph. It also avoids communication obstructions as everyone will know whom they are supposed to report to in case of any troubles or situations that are uncontrollable takes place.

### 13) Delegation

Delegation implies that the subordinate is been given the authority to do a job he or she can make independent decisions but delegation does not mean that the final responsibility is on the person who the work is been delegated it is on the person who is delegating the work. Delegation is done to save time, money and to motivate the subordinate. Delegation helps in splitting huge time consuming and tough works to be carried out easily as its work load is divided between two or more people.

The tasks that are delegated are mentioned in the table below.

| Task Description | Task delegated to |
| --- | --- |
| Task 1 | 1 TM 1 TL and 2 TECH and principal |
| Task2 PART A | 1 TM 3 TECH |
| Task2 PART B | 1 TL 3 TECH |
| Task3 | 1TM 1TL |
| Task4 | 1TM 1TECH 1 Professional designer and 1TL and principal |

Figure 1.8: Delegation of tasks for the project

TM =team members

TL= team leader

Tech= teacher

### 14) Types of communication

Communication is when two or more people conversing, communicating their feelings toward one another, and eventually understanding each other. It is very essential for project team members to communicate well enough to each others to let the other team members know the current position of the task and what they have to do to complete the task.

There are some of communication systems that are applicable in this project those are

- Electronic communication - as seeing the time period of this project that is 2 months that is very short period of time there should be more and more use of fast and effective manner of communication and the best suited communication is mobile phones, emails, faxes, pager and etc. This is the most vital way of communication as it saves money as well as time.

- Face to face communication- there are many things that are not to be discussed or talks that should take place in between two or more people face to face because of the trusted factor of not letting the words get licked  in the public matters like money, problems and many more.

### 15) Success / Failure Criteria

The probability of the success of this Magazine project are high as every element necessary for the project to be successful are enclosed and stated below for the person to carry out in this project. The only reasons for any breakdown for this project could be caused due to a delay in undertaking the tasks or if the tasks are not carried out appropriately. Solutions to overcome these problems are mentioned in the Risk-Assessment Table.

### 16) Motivation

“Motivation is the processes that account for an individual's intensity, direction, and persistence of effort toward attaining a goal”. -Robbins, 2004

Motivation is a factor that inspires a person to achieve the goals or the objectives that has put up by the project. If the team member of the project are motivated fully then the members will feel more importance for the tasks and will work more efficiently and give a good performance that will help the project to finish it goal. However, if the motivation is not taken proper care then the workers can feel unwilling to work efficiently in the project creating a deprived performance and failure in the project.

There are some benefits of motivation and drawbacks of non-motivation.

| Motivation | Non motivation |
| --- | --- |
| More effective work of the worker Less wastage done from the workers The best productivity will be produced in terms of service and goods Less holidays will be taken from the workers Less workers turnover Workers will take responsibility | More workers turnover Workers may not take the orders Poor performance More absenteeism Uncomfortable situation will occur between the management and the workers. |

Since this project will get over within a span of 57 days, most of the team members working will be on a part-time basis. Thus, the financial rewards would be an excellent way to motivate teachers to undertake their task effectively. They could be given a performance related additional pay on 10% on basis of monthly salary. If their performance towards the work is productive then they will earn the benefit of this scheme.

The non - financial rewards for students such as certificates of participation in the school activity also there can be an award to be given to the student on annual day to appreciate the student's work in front of the whole school.

### 17) Leadership styles

“A good leader is a master key to every lock”

The above sentence means that a good leader brings in different quality of leaderships leading to different solution to different problems”.

(Anonymous)

### According to Peter drucker, “Leadership is having followers who "do the right thing.”

The author evaluates the two definitions, and says that leadership is the main issue an organization should consider. Leadership is the brain of the company it has to have a matter of making a difference.  It requires making an active choice among many possible substitutes. In addition, it depends on involving the low-level management along in the judgment.

As the project demand for creativity the type of leadership style adapted by the Project Manager should be the laissez - faire style. This style is been used when the managers delegate all the decision making for undertaking a task on the lower level. The leadership style adapted by the Project Manager should be the laissez - faire style. This style is used when the managers delegate all the decision making for undertaking a task on the lower level.

Some workers may not appreciate the structure and may not be good decision makers that could lead to incompletion of the task. They may also be de-motivated if there is no one monitoring them. Thus the team leaders must monitor them as well.

### 18) Closure of the Project and Appraisal

The project is looked from the Initiation stage until the bottom stage that is Execution. In this phase the project is been under the evaluation to conclude the extent to which the project is been successful and any other lesson that is been learnt during the project for the future projects. The project report is been made to have an record of events and experiences that are been shared with others team members and the other non working staffs. To ensure that the project closure is been undertaken smoothly and efficiently there is an action taken place that is Post Implementation Review. In this the higher level of the staff do the needful in this case it is the principal and the teachers are the people who look after the extent of the success of the project and ensure the benefit achieved by the project and then finally the project is been closed out.

### 19) Conclusion

The manager and the team members of the project saw the project successful as the main pupose of starting the project was been achieved. The project was been done successfully due to the on time completion of the project within the given budget and meeting the expectation of the school and college. The objectives of the project were clear making each team member of project motivated and going into the right direction of completing the project on time.

Lastly, I would conclude by saying that I had a great experience working with such an experienced team and it improved my planning skills, leadership skills, communication skills and my research skills.